## HOW TO USE
HOW TO USE - 3 simple steps
STEP 1 - Team | Go to UPDATE STATS. Add one row each time you have new numbers (daily or weekly): pick Date, Client, Campaign, Channel, Your Name, then type only the numbers that apply (emails, leads, spend...). Numbers are for THAT period - not running totals.
STEP 2 - Campaign owners | On CAMPAIGNS keep Status (Planned / Live / Paused / Completed), dates and Leads Target up to date. Leads, MQLs and spend appear on their own.
STEP 3 - Programs (optional) | On PROGRAM STATUS just change the Status when something moves: Not Started / In Progress / Done / Blocked. No daily tasks needed.
Manager | Open DASHBOARD. Pick Month and Client at the top. Everything else updates by itself.
Colours | BLUE = you type or pick. GREY = automatic, do not type. DASHBOARD is locked (no password) so nothing breaks.
Do not | Rename sheets or column headings, or delete columns. If a campaign is renamed, change it everywhere.
New client / campaign / person | Add on CLIENTS, CAMPAIGNS or LISTS (team). They appear in the dropdowns straight away.
Running out of rows? | Copy the last row (blue and grey cells) and paste below it.
Open Rate | Opens / Emails Sent
Click Rate | Clicks / Emails Sent
Cost per Lead | Ad Spend / Leads
Lead > MQL % | MQLs / Leads
Check column (Campaigns) | Update needed = Live campaign with no stats for 7+ days. Behind target = under 50% of Leads Target. No stats yet = Live but nothing entered.
Leads counted twice? | Enter each lead count once - one row per Campaign per period.

## DASHBOARD
DIGITAL MARKETING DASHBOARD
Updates automatically from UPDATE STATS. Nothing to type here except the 3 blue boxes below.
MONTH |  |  | CLIENT |  |  | AS OF DATE |  |  |  | <>@@
All |  |  | All |  |  | 2026-10-05 |  |  |  | <>@@
RESULTS (for the Month and Client selected above)
LEADS |  | HANDRAISERS |  | MQLs |  | SQLs |  | OPPORTUNITIES |  | LEAD > MQL %
0 |  | 0 |  | 0 |  | 0 |  | 0 |  | -
EMAILS SENT |  | OPEN RATE |  | CLICK RATE |  | REPLIES |  | AD SPEND |  | COST PER LEAD
0 |  | - |  | - |  | 0 |  | 0 |  | -
NEEDS ATTENTION
LIVE CAMPAIGNS |  | NEED A STATS UPDATE |  | BEHIND TARGET |  | PROGRAMS BLOCKED |  | STATUS NOT UPDATED |  | PROGRAMS DONE
0 |  | 0 |  | 0 |  | 0 |  | 58 |  | 0
Blocked programs |  |  |  | Client |  | Team Member |  | Remark / Next Step
- none -
BY CLIENT (Month filter applies) - Tata Communications / MECCA highlighted
Client |  | Status | Leads | MQLs | SQLs | Emails Sent | Open Rate | Ad Spend | Cost / Lead | Programs Blocked
Chola MS |  | Active | 0 | 0 | 0 | 0 |  | 0 |  | 0
Magnasoft |  | Active | 0 | 0 | 0 | 0 |  | 0 |  | 0
Eternelle |  | Active | 0 | 0 | 0 | 0 |  | 0 |  | 0
Vestrics |  | Active | 0 | 0 | 0 | 0 |  | 0 |  | 0
Lenovo |  | Active | 0 | 0 | 0 | 0 |  | 0 |  | 0
SAP |  | Active | 0 | 0 | 0 | 0 |  | 0 |  | 0
Tata Communications |  | Active | 0 | 0 | 0 | 0 |  | 0 |  | 0
Tata Communications MECCA |  | Active | 0 | 0 | 0 | 0 |  | 0 |  | 0
Salesforce |  | Active | 0 | 0 | 0 | 0 |  | 0 |  | 0
Ruckus Networks |  | Active | 0 | 0 | 0 | 0 |  | 0 |  | 0
Google Chrome Enterprise |  | Active | 0 | 0 | 0 | 0 |  | 0 |  | 0
Equinix |  | Active | 0 | 0 | 0 | 0 |  | 0 |  | 0
Sonalika Tractors |  | Pipeline | 0 | 0 | 0 | 0 |  | 0 |  | 0
AMEX |  | Pipeline | 0 | 0 | 0 | 0 |  | 0 |  | 0
Marg Business Transformation |  | Ended | 0 | 0 | 0 | 0 |  | 0 |  | 0
Utimaco Singapore |  | To Confirm | 0 | 0 | 0 | 0 |  | 0 |  | 0
LAST 6 MONTHS (Client filter applies)
Month |  | 2026-05 | 2026-06 | 2026-07 | 2026-08 | 2026-09 | 2026-10
| Leads | 0 | 0 | 0 | 0 | 0 | 0
| MQLs | 0 | 0 | 0 | 0 | 0 | 0
| SQLs | 0 | 0 | 0 | 0 | 0 | 0
| Emails Sent | 0 | 0 | 0 | 0 | 0 | 0
| Ad Spend | 0 | 0 | 0 | 0 | 0 | 0
TEAM - PROGRAM STATUS (who is working on what)
Team Member |  | Role |  |  | Programs | Not Started | In Progress | Done | Blocked | Not Updated
Ayush Jain |  | Program Manager |  |  | 16 | 0 | 0 | 0 | 0 | 16
Piyush Sambria |  | Creative Lead |  |  | 0 | 0 | 0 | 0 | 0 | 0
Riya Diwan |  | Program Execution Expert |  |  | 16 | 0 | 0 | 0 | 0 | 16
Surbhi Pandey |  | Program Execution Expert |  |  | 19 | 0 | 0 | 0 | 0 | 19
Rahul Sondhi |  | Video Lead |  |  | 0 | 0 | 0 | 0 | 0 | 0
Priyanshu |  | Content Lead |  |  | 0 | 0 | 0 | 0 | 0 | 0
Richi Bagla |  | Paid Ads Specialist / Program Manager |  |  | 7 | 0 | 0 | 0 | 0 | 7
Kapil Chadha |  | Consultant - SEO |  |  | 0 | 0 | 0 | 0 | 0 | 0
CAMPAIGNS (all-time results from UPDATE STATS)
Campaign |  | 2026-07: Client; 2026-09: Owner; 2026-10: Status | Leads | Target | Check
SAP Partner Campaign - Citek |  | 2026-07: SAP; 2026-09: Surbhi Pandey | 0
SAP Partner Campaign - Apptech |  | 2026-07: SAP; 2026-09: Surbhi Pandey | 0
SAP Partner Campaign - Netizen |  | 2026-07: SAP; 2026-09: Surbhi Pandey | 0
SAP Partner Campaign - Ikyam |  | 2026-07: SAP; 2026-09: Surbhi Pandey | 0
SAP Partner Campaign - Castaliaz |  | 2026-07: SAP; 2026-09: Surbhi Pandey | 0
SAP Partner Campaign - Truspeq |  | 2026-07: SAP; 2026-09: Surbhi Pandey | 0
SAP Partner Campaign - NTT Data |  | 2026-07: SAP; 2026-09: Surbhi Pandey | 0
SAP Partner Campaign - Abeam TH |  | 2026-07: SAP; 2026-09: Surbhi Pandey | 0
Utimaco Singapore |  | 2026-07: Utimaco Singapore; 2026-09: Surbhi Pandey | 0
SAP Success Factor HR Bengaluru |  | 2026-07: SAP; 2026-09: Surbhi Pandey | 0
SAP Viksit Bharat |  | 2026-07: SAP; 2026-09: Surbhi Pandey | 0
SAP Success Factor Delhi |  | 2026-07: SAP; 2026-09: Surbhi Pandey | 0
SAP HRMS |  | 2026-07: SAP; 2026-09: Surbhi Pandey | 0
Vestrics - Google Ads |  | 2026-07: Vestrics; 2026-09: Richi Bagla | 0
Eternelle - Google Ads |  | 2026-07: Eternelle; 2026-09: Richi Bagla | 0
Magnasoft - Google Ads |  | 2026-07: Magnasoft; 2026-09: Richi Bagla | 0
Ruckus - Content Syndication (Email) |  | 2026-07: Ruckus Networks; 2026-09: Richi Bagla | 0 | 50
Equinix - Content Syndication (Email) |  | 2026-07: Equinix; 2026-09: Richi Bagla | 0 | 150
Google Chrome - Content Syndication (Email) |  | 2026-07: Google Chrome Enterprise; 2026-09: Riya Diwan | 0
Chola MS - SEO & Social Media |  | 2026-07: Chola MS; 2026-09: Ayush Jain | 0
Vestrics - SEO & Social Media |  | 2026-07: Vestrics; 2026-09: Ayush Jain | 0
Magnasoft - SEO & Social Media |  | 2026-07: Magnasoft; 2026-09: Ayush Jain | 0
Eternelle - SEO & Blogs |  | 2026-07: Eternelle; 2026-09: Richi Bagla | 0
Lenovo - Email Deployment |  | 2026-07: Lenovo | 0
Sonalika Tractors - Meta Automation |  | 2026-07: Sonalika Tractors | 0
Tata MECCA Campaign |  | 2026-07: Tata Communications MECCA | 0

## UPDATE STATS
UPDATE STATS - enter your numbers here
BLUE cells = team enters data ¦ GREY cells = automatic formulas (do not edit) ¦ One row per update (daily or weekly). Fill only what applies. Enter numbers for THAT period, not running totals.
Example: 05-Oct-26 ¦ SAP ¦ SAP Viksit Bharat ¦ Email ¦ Surbhi Pandey ¦ 5000 ¦ 900 ¦ 120 ¦ 20 ¦ 0 ¦ 2 ¦ 25 ¦ 6 ¦ 1 ...
Date | Client | Campaign | Channel | Your Name | Emails Sent | Opens | Clicks | Replies | Ad Spend | Handraisers | Leads | MQLs | SQLs | Opportunities | Notes | Open Rate | Click Rate | Cost per Lead | Month

## CAMPAIGNS
CAMPAIGNS - one row per campaign
BLUE cells = team enters data ¦ GREY cells = automatic formulas (do not edit) ¦ Fill the blue columns. Leads, MQLs and spend fill in automatically from UPDATE STATS.
Client | Campaign Name | Channel | Owner | Status | Start Date | End Date | Leads Target | Remarks | Leads So Far | MQLs So Far | Spend So Far | % of Target | Last Stats Entry | Check
SAP | SAP Partner Campaign - Citek | Content Syndication | Surbhi Pandey |  |  |  |  | Content Syndication - Email. Status/dates not provided in baseline. | 0 | 0 | 0
SAP | SAP Partner Campaign - Apptech | Content Syndication | Surbhi Pandey |  |  |  |  | Content Syndication - Email. Status/dates not provided in baseline. | 0 | 0 | 0
SAP | SAP Partner Campaign - Netizen | Content Syndication | Surbhi Pandey |  |  |  |  | Content Syndication - Email. Status/dates not provided in baseline. | 0 | 0 | 0
SAP | SAP Partner Campaign - Ikyam | Content Syndication | Surbhi Pandey |  |  |  |  | Content Syndication - Email. Status/dates not provided in baseline. | 0 | 0 | 0
SAP | SAP Partner Campaign - Castaliaz | Content Syndication | Surbhi Pandey |  |  |  |  | Content Syndication - Email. Status/dates not provided in baseline. | 0 | 0 | 0
SAP | SAP Partner Campaign - Truspeq | Content Syndication | Surbhi Pandey |  |  |  |  | Content Syndication - Email. Status/dates not provided in baseline. | 0 | 0 | 0
SAP | SAP Partner Campaign - NTT Data | Content Syndication | Surbhi Pandey |  |  |  |  | Content Syndication - Email. Status/dates not provided in baseline. | 0 | 0 | 0
SAP | SAP Partner Campaign - Abeam TH | Content Syndication | Surbhi Pandey |  |  |  |  | Content Syndication - Email. Status/dates not provided in baseline. | 0 | 0 | 0
Utimaco Singapore | Utimaco Singapore | Content Syndication | Surbhi Pandey |  |  |  |  | Content Syndication - Email. | 0 | 0 | 0
SAP | SAP Success Factor HR Bengaluru | Content Syndication | Surbhi Pandey |  |  |  |  | Email + WhatsApp. Deployments: 25th Sep and 9th Oct (year assumed 2026). | 0 | 0 | 0
SAP | SAP Viksit Bharat | Content Syndication | Surbhi Pandey |  |  |  |  | Email + WhatsApp. Deployments: 25th Sep and 6th Oct (year assumed 2026). | 0 | 0 | 0
SAP | SAP Success Factor Delhi | Content Syndication | Surbhi Pandey |  |  |  |  | Email + WhatsApp. Deployment: 30th Sep (year assumed 2026). | 0 | 0 | 0
SAP | SAP HRMS | LinkedIn Outreach | Surbhi Pandey |  |  |  |  | Dripify & Sales Navigator. | 0 | 0 | 0
Vestrics | Vestrics - Google Ads | Google Ads | Richi Bagla |  |  |  |  | Target as provided: 10-15 leads in a month. | 0 | 0 | 0
Eternelle | Eternelle - Google Ads | Google Ads | Richi Bagla |  |  |  |  | Target as provided: 8-10 leads daily. | 0 | 0 | 0
Magnasoft | Magnasoft - Google Ads | Google Ads | Richi Bagla |  |  |  |  | Target: 'No update' in Project Updates. | 0 | 0 | 0
Ruckus Networks | Ruckus - Content Syndication (Email) | Content Syndication | Richi Bagla |  |  |  | 50 | Target: 50 form fills (Project Updates); 50 leads over 3 months (billing sheet). | 0 | 0 | 0 | 0%
Equinix | Equinix - Content Syndication (Email) | Content Syndication | Richi Bagla |  |  |  | 150 | Target: 150 form fills (Project Updates); 150 leads by Dec'26 (billing sheet). | 0 | 0 | 0 | 0%
Google Chrome Enterprise | Google Chrome - Content Syndication (Email) | Content Syndication | Riya Diwan |  |  |  |  | Reporting needs: form fills, opens/clicks data. | 0 | 0 | 0
Chola MS | Chola MS - SEO & Social Media | Multi-channel | Ayush Jain |  |  |  |  | Ongoing retainer programme. Target as provided: 38-40 leads and 22 posts (Riya's sheet). | 0 | 0 | 0
Vestrics | Vestrics - SEO & Social Media | Multi-channel | Ayush Jain |  |  |  |  | Ongoing retainer programme. | 0 | 0 | 0
Magnasoft | Magnasoft - SEO & Social Media | Multi-channel | Ayush Jain |  |  |  |  | Ongoing retainer programme. | 0 | 0 | 0
Eternelle | Eternelle - SEO & Blogs | Multi-channel | Richi Bagla |  |  |  |  | Ongoing retainer programme. Target as provided: 6 blogs a month. | 0 | 0 | 0
Lenovo | Lenovo - Email Deployment | Email | [5 empty] | No update provided by team. | 0 | 0 | 0
Sonalika Tractors | Sonalika Tractors - Meta Automation | Meta Ads | [5 empty] | Proposal stage. No update provided yet. | 0 | 0 | 0
Tata Communications MECCA | Tata MECCA Campaign | Multi-channel | [5 empty] | Campaign listed in Team Details (Priyanshu). No other details provided. | 0 | 0 | 0

## PROGRAM STATUS
PROGRAM STATUS - who is working on what (update when status changes)
BLUE cells = team enters data ¦ GREY cells = automatic formulas (do not edit) ¦ Not a daily task list - just change Status when a program moves (Not Started > In Progress > Done / Blocked).
Team Member | Client | Program / Work | Target (as provided) | Status | Date (if any) | Remark / Next Step | Blocked key
Surbhi Pandey | SAP | Content Syndication - Email [SAP Partner Campaign - Citek]
Surbhi Pandey | SAP | Content Syndication - Email [SAP Partner Campaign - Apptech]
Surbhi Pandey | SAP | Content Syndication - Email [SAP Partner Campaign - Netizen]
Surbhi Pandey | SAP | Content Syndication - Email [SAP Partner Campaign - Ikyam]
Surbhi Pandey | SAP | Content Syndication - Email [SAP Partner Campaign - Castaliaz]
Surbhi Pandey | SAP | Content Syndication - Email [SAP Partner Campaign - Truspeq]
Surbhi Pandey | SAP | Content Syndication - Email [SAP Partner Campaign - NTT Data]
Surbhi Pandey | SAP | Content Syndication - Email [SAP Partner Campaign - Abeam TH]
Surbhi Pandey | Utimaco Singapore | Content Syndication - Email [Utimaco Singapore]
Surbhi Pandey | SAP | Content Syndication - Email + WhatsApp deployment [SAP Success Factor HR Bengaluru] |  |  | 2026-09-25 | Date as provided: '25th Sep' (year assumed 2026 - please confirm).
Surbhi Pandey | SAP | Content Syndication - Email + WhatsApp deployment [SAP Success Factor HR Bengaluru] |  |  | 2026-10-09 | Date as provided: '9th Oct' (year assumed 2026 - please confirm).
Surbhi Pandey | SAP | Content Syndication - Email + WhatsApp deployment [SAP Viksit Bharat] |  |  | 2026-09-25 | Date as provided: '25th Sep' (year assumed 2026 - please confirm).
Surbhi Pandey | SAP | Content Syndication - Email + WhatsApp deployment [SAP Viksit Bharat] |  |  | 2026-10-06 | Date as provided: '6th Oct' (year assumed 2026 - please confirm).
Surbhi Pandey | SAP | Content Syndication - Email + WhatsApp deployment [SAP Success Factor Delhi] |  |  | 2026-09-30 | Date as provided: '30th Sep' (year assumed 2026 - please confirm).
Surbhi Pandey | SAP | Dripify & Sales Navigator [SAP HRMS]
Surbhi Pandey | SAP | SAP Events Intent Report
Surbhi Pandey | SAP | SAP Partner Campaign Report & Dashboard
Surbhi Pandey | SAP | Create EDM HTML and work on EDM content
Surbhi Pandey | SAP | SAP Events WhatsApp Templates
Richi Bagla | Vestrics | Google Ads [Vestrics - Google Ads] | 10-15 leads in a month
Richi Bagla | Eternelle | Google Ads [Eternelle - Google Ads] | 8-10 leads daily
Richi Bagla | Eternelle | Client Co-ordination
Richi Bagla | Magnasoft | Google Ads [Magnasoft - Google Ads] | No update
Richi Bagla | Ruckus Networks | Content Syndication - Email [Ruckus - Content Syndication (Email)] | 50 form fills
Richi Bagla | Equinix | Content Syndication - Email [Equinix - Content Syndication (Email)] | 150 form fills
Richi Bagla | SAP | Helping Surbhi with landing pages
Riya Diwan | Chola MS | Client coordination [Chola MS - SEO & Social Media]
Riya Diwan | Chola MS | Social postings (approval and internal coordination) [Chola MS - SEO & Social Media] | 38-40 leads; 22 posts
Riya Diwan | Chola MS | SEO (on page, content & link building) [Chola MS - SEO & Social Media]
Riya Diwan | Chola MS | Website management & updates [Chola MS - SEO & Social Media]
Riya Diwan | Chola MS | Monthly report [Chola MS - SEO & Social Media]
Riya Diwan | Google Chrome Enterprise | Content Syndication - Email [Google Chrome - Content Syndication (Email)] | Form fills; opens/clicks data
Riya Diwan | Google Chrome Enterprise | Leads update and map data [Google Chrome - Content Syndication (Email)]
Riya Diwan | Vestrics | Blog posting [Vestrics - SEO & Social Media]
Riya Diwan | Vestrics | Off page SEO (content & link building) [Vestrics - SEO & Social Media]
Riya Diwan | Vestrics | Social postings [Vestrics - SEO & Social Media]
Riya Diwan | Vestrics | Monthly report [Vestrics - SEO & Social Media]
Riya Diwan | Magnasoft | Blog posting [Magnasoft - SEO & Social Media]
Riya Diwan | Magnasoft | Social postings [Magnasoft - SEO & Social Media]
Riya Diwan | Magnasoft | Off page SEO (content & link building) [Magnasoft - SEO & Social Media]
Riya Diwan | Eternelle | Blog posting [Eternelle - SEO & Blogs] | 6 blogs a month
Riya Diwan | SAP | Help Ayush in EDM (HTML) | Whenever needed
Ayush Jain | Chola MS | Content calendar preparation [Chola MS - SEO & Social Media] | Mandate: 22
Ayush Jain | Chola MS | Off page & on page content research [Chola MS - SEO & Social Media] | Mandate: 8
Ayush Jain | Vestrics | Client co-ordination
Ayush Jain | Vestrics | Helping Richi in running ads [Vestrics - Google Ads]
Ayush Jain | Vestrics | Social media calendar preparation [Vestrics - SEO & Social Media] | Mandate: 10-12
Ayush Jain | Vestrics | Internal team co-ordination
Ayush Jain | Vestrics | Off page & on page content research [Vestrics - SEO & Social Media] | Mandate: 4
Ayush Jain | Vestrics | Website management & SEO [Vestrics - SEO & Social Media]
Ayush Jain | Magnasoft | Client co-ordination
Ayush Jain | Magnasoft | Internal team co-ordination
Ayush Jain | Magnasoft | Content topic research [Magnasoft - SEO & Social Media] | Mandate: 8
Ayush Jain | Magnasoft | Website management [Magnasoft - SEO & Social Media]
Ayush Jain | Magnasoft | Social media calendar preparation [Magnasoft - SEO & Social Media] | Mandate: 10-12
Ayush Jain | Eternelle | Content research [Eternelle - SEO & Blogs] | Mandate: 8
Ayush Jain | Eternelle | Ads planning [Eternelle - Google Ads]
Ayush Jain | Google Chrome Enterprise | Team co-ordination

## CLIENTS
CLIENTS - one row per client
BLUE cells = team enters data ¦ GREY cells = automatic formulas (do not edit) ¦ Add a new client here first - it then appears in all dropdowns.
Client | Status | Type | Services | Notes
Chola MS | Active | External | SEO ¦ Social Media Management
Magnasoft | Active | External | SEO ¦ Social Media Management ¦ Paid Ads | Website Revamp proposal in pipeline (priority High, 90 days).
Eternelle | Active | External | SEO ¦ Paid Ads
Vestrics | Active | External | SEO ¦ Creative Mandate ¦ Paid Ads ¦ Social Media Management
Lenovo | Active | External | Email Deployment | Lenovo EDM proposal in pipeline (High @90, 14 weeks). No update received from team on Lenovo.
SAP | Active | Internal | Email Deployment | Also: SAP Drip Campaigns - Install Base (Internal, Active). Alignment (BDMIS) yet to be done per billing sheet.
Tata Communications | Active | Internal | Not Available | Alignment (BDMIS) yet to be done per billing sheet.
Tata Communications MECCA | Active | Internal | Not Available | Alignment (BDMIS) yet to be done per billing sheet.
Salesforce | Active | Internal | Not Available | Validity: TBD per billing sheet.
Ruckus Networks | Active | External | Email creation & Landing Page | TO CONFIRM: billing sheet marks this 'Closed' but team is actively working it (50 form-fill target).
Google Chrome Enterprise | Active | Internal | Email Deployment | TO CONFIRM: billing sheet marks this 'Closed' with validity to 1-Oct-2026; team still reporting work.
Equinix | Active | Internal | Email creation & Landing Page | TO CONFIRM: billing sheet marks this 'Closed'; team actively working it (150 form-fill target).
Sonalika Tractors | Pipeline | External | Meta Automation | Proposal stage, priority High, monthly retainer. No BDMIS alignment. No update from team yet.
AMEX | Pipeline | External | Email Deployment | Email deployment planned Nov & Dec (proposal marked 'Closed'; high @90, no BDMIS alignment).
Marg Business Transformation | Ended | External | Digital Marketing | Engagement closed. Last day: 11 September.
Utimaco Singapore | To Confirm |  | Content Syndication - Email | Listed in Surbhi's program list only; client/commercial status not in billing sheet.

## LISTS
LISTS - team and dropdown options (manager updates)
Add new items at the bottom of a list (no gaps). Clients are added on the CLIENTS sheet, campaigns on CAMPAIGNS.
Team Member | Role | Channel | Campaign Status | Program Status | Client Status | Month filter | Client filter (auto)
Ayush Jain | Program Manager | Email | Planned | Not Started | Active | All | All
Piyush Sambria | Creative Lead | Content Syndication | Live | In Progress | Pipeline | 2025-01 | Chola MS
Riya Diwan | Program Execution Expert | WhatsApp | Paused | Done | Ended | 2025-02 | Magnasoft
Surbhi Pandey | Program Execution Expert | LinkedIn Outreach | Completed | Blocked | To Confirm | 2025-03 | Eternelle
Rahul Sondhi | Video Lead | Google Ads |  |  |  | 2025-04 | Vestrics
Priyanshu | Content Lead | Meta Ads |  |  |  | 2025-05 | Lenovo
Richi Bagla | Paid Ads Specialist / Program Manager | LinkedIn Ads |  |  |  | 2025-06 | SAP
Kapil Chadha | Consultant - SEO | SEO |  |  |  | 2025-07 | Tata Communications
|  | Social Media |  |  |  | 2025-08 | Tata Communications MECCA
|  | Website |  |  |  | 2025-09 | Salesforce
|  | Multi-channel |  |  |  | 2025-10 | Ruckus Networks
|  | Other |  |  |  | 2025-11 | Google Chrome Enterprise
[6 empty] | 2025-12 | Equinix
[6 empty] | 2026-01 | Sonalika Tractors
[6 empty] | 2026-02 | AMEX
[6 empty] | 2026-03 | Marg Business Transformation
[6 empty] | 2026-04 | Utimaco Singapore
2026-05
2026-06
2026-07
2026-08
2026-09
2026-10
2026-11
2026-12
2027-01
2027-02
2027-03
2027-04
2027-05
2027-06
2027-07
2027-08
2027-09
2027-10
2027-11
2027-12